## Summary
Systemic Advisory – Post-Closing Integration Plan
Purpose: Ensure seamless operational, cultural, and compliance integration following acquisition.
Scope: Behavioral-health and outpatient healthcare services platform integration.
Timeline:
0–30 Days – Stabilization
31–90 Days – Transition
91–180 Days – Optimization
Key Leadership Roles:
Buyer CEO – Executive Sponsor
COO – Integration Lead
HR Director – People & Culture
Compliance Officer – Clinical & Regulatory Oversight
CFO – Finance & RCM
IT Director – Systems & Data Security
Guiding Principles:
1. Continuity of patient care and clinician trust
2. Transparency in communication
3. Compliance with all licensure and payer requirements
4. Preservation of culture and morale
5. Timely value capture

## Governance & Communication
Area | Action Item | Responsible Party | Target Date | Status | Notes
Governance | Form Integration Steering Committee | COO | Day 1
Communication | Create 90-Day Communication Plan | HR Director | Day 5
Reporting | Establish Weekly Progress Reviews | COO | Ongoing
Stakeholder Alignment | Conduct Kick-off with Seller Leadership | Buyer CEO | Week 1
Documentation | Maintain Central Integration Tracker | Project Manager | Ongoing

## Operations & Facilities
Area | Action Item | Responsible Party | Target Date | Status | Notes
Branding | Update signage, forms, and email templates | Ops Director | 30 Days
Leases | Confirm transfer and payment of facility leases | Real Estate Lead | 15 Days
Vendors | Migrate vendor contracts to Buyer entity | Procurement | 45 Days
Insurance | Validate property and liability coverage under Buyer | Risk Manager | 30 Days
Supplies | Align clinical supply ordering systems | Ops Coordinator | 45 Days

## HR & Culture
Area | Action Item | Responsible Party | Target Date | Status | Notes
Onboarding | Add all staff to Buyer HRIS and payroll | HR Manager | Week 2
Benefits | Transition benefits, PTO, and bonus plans | HR Manager | 60 Days
Culture | Host welcome events and leadership Q&A | HR Director | 30 Days
Policies | Harmonize HR policies and employee handbook | HR Director | 45 Days
Retention | Identify and support key clinicians | COO | Ongoing

## Clinical & Compliance
Area | Action Item | Responsible Party | Target Date | Status | Notes
Licensure | Transfer facility and clinician licenses | Compliance Officer | 45 Days
Credentialing | Submit change-of-ownership documents to payors | Credentialing Lead | 30 Days
QA & HIPAA | Conduct post-close QA/HIPAA audit | Compliance Officer | 60 Days
Policy Integration | Align clinical documentation and protocols | Medical Director | 60 Days
Audit Prep | Verify compliance logs and incident reports | Compliance Team | 90 Days

## Finance & Revenue Cycle
Area | Action Item | Responsible Party | Target Date | Status | Notes
Accounting | Integrate chart of accounts and bank accounts | CFO | 30 Days
Billing | Migrate billing platform / clearinghouse | RCM Director | 45 Days
Payors | Send ownership notification letters | Finance / RCM | 30 Days
AR Review | Validate pre- and post-close receivables | Controller | 60 Days
Payroll | Align payroll schedules and tax filings | HR / Finance | 15 Days

## IT & Systems
Metric | Definition | Baseline | Target (90 Days) | Status | Notes
Clinician Retention | % of pre-close clinicians retained |  | 95%
Revenue Continuity | % of pre-close monthly revenue maintained |  | 100%
Denial Rate | % of claims denied post-transition |  | <5%
License Transfers Complete | % of licenses successfully transitioned |  | 100%
Staff Satisfaction | Avg. survey score (1-5) |  | ≥4.0

## KPIs
Metric | Definition | Baseline | Target (90 Days) | Status | Notes
Clinician Retention | % of pre-close clinicians retained |  | 95%
Revenue Continuity | % of pre-close monthly revenue maintained |  | 100%
Denial Rate | % of claims denied post-transition |  | <5%
License Transfers Complete | % of licenses successfully transitioned |  | 100%
Staff Satisfaction | Avg. survey score (1-5) |  | ≥4.0